## Implementation Plan
RECOMMENDATION IMPLEMENTATION PROJECT PLAN |  |  |  | Smartsheet Tip ➜ | [5 empty] | This is a modified form of a Gantt chart which focuses on creating a project schedule that is broken down into stages.
PROJECT TITLE |  | [Project's title] |  | OPERATING UNIT (OU) | [6 empty] | [OU Name]
PROJECT MANAGER |  | [Project Manager's name] |  | DATE | [6 empty] | 2018-03-12
|  |  |  | Q1 | [10 empty] | Q2 |  |  |  | Q3 |  |  |  | Q4
|  |  |  | OCT |  |  |  |  | NOV |  |  |  | DEC |  | JAN | FEB |  | MAR | APR |  | MAY | JUN | JUL | AUG | SEP
| PHASE |  | TASK: Enter the date of the first Monday of each month --> | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27
1 | Milestones & Meetings |  | - Initial Meeting Post OER Report | OCT 16: Example Dates for Initial Meeting Post OER Report | [7 empty] | EXAMPLE PROJECT END
|  |  | - Mid-point Meeting | NOV 13: Example Task
|  |  | - Other Milestone or Meeting | [10 empty] | Example Task
|  |  | - Other Milestone or Meeting | [10 empty] | Example Task
|  |  | - Project Close | [10 empty] | Example Task
2 | Recommendation 1 (Example: Hire 1 USDH Deputy Controller) |  | - Task (Example: Draft a Position Description for USAJobs.gov) | [11 empty] | Example Task
|  |  | - Task | [13 empty] | Example Task
- Task
- Task
- Task
- Task
3 | Recommendation 2 |  | - Task
- Task
- Task
- Task
4 | Recommendation 3 |  | - Task
- Task
- Task
- Task
5 | Recommendation 4 |  | - Task
- Task
- Task
- Task

## Tracking Tool
Phase | Task Type | Recommendation (if Applicable) | Task Description | Start Date (MM/DD/YY) | End Date (MM/DD/YY) | Responsible Unit | Point of Contact | Supporting Unit/Technical Assistance Provider(s) | Status | Other Information
Milestones & Meetings | Meeting | Not Applicable | Intial Meeting after receiving OER recommendations | 2021-02-23 | 2021-02-23 | Mission Director's Office | Candice Nguyen | N/A | Completed
Recommendation 1: Hire 1 USDH Deputy Controller | Recommendation Implementation | 1.1 | Draft a position description for USAJobs.gov | 2021-08-24 | 2022-08-01 | Support Services | Devon Franklin | HCTM | Not Started

## Key
Key Project Term | Attributes
Phase | - Key area of work - Tracking Tool data should correspond with Project Plan data
Task Type | - Type of work within a phase to address - Includes meetings, recommendations and milestones
Recommendation (if Applicable) | - An indication of which MMA recommendation the task is connected to
Task | - A short summation of the step being taken to implement the project plan - There are multiple tasks for one phase - Tracking Tool data should correspond with Project Plan data
Task Description | - Detailed information about the task - Includes the tasks objective(s) - May be extensive or relatively short
Start Date (MM/DD/YY) | - Indicates beginning of task related work - Tracking Tool data should correspond with Project Plan data
End Date (MM/DD/YY) | - Indicates conclusion of task related work - Tracking Tool data should correspond with Project Plan data
Responsible Unit | - Bureau, office, team or other entity responsible for implementing task - Manages completion of task - Provides staff to implement the task - May recruit and manage other entities to complete the task
Point of Contact | - Individual to contact about the task's status and overall implementation - Represents the Responsible Unit - May act as task manager - Responsible for reporting task status
Supporting Unit/Technical Assistance Provider(s) | - Communicates with Responsible Unit and POC to provide technical assistance to Mission/OU in implementing recommendations
Status | - Communicates with Responsible Unit and POC to provide technical assistance to Mission/OU in implementing recommendations
Other Information | - Space to provide additional information about task implementation - May be used to provide information about costs - May refer to contingencies in planning - May be used to elaborate on why task has a particular status